## Tabelle1
Timetable TF2 (Jordyn) |  | Alternative Timetable TF2
2003-12-18 | Data Collection Starts | 2003-12-18 | Data Collection Starts
27 days | Collection of Data from Constituencies the GAC and CCNSO | 43 days | Collection of Data from Constituencies the GAC and CCNSO + creation of an interim report
2003-01-15 | Interim report on collected data | 2003-01-31 | Interim report on collected data
10 days | Public comment Period on Interim report | 10 days | Public comment Period on Interim report and collected data
2003-01-25 | End Public Comment | 2003-02-10 | End Public Comment
7 days | compilaton of collected data an public comment | 10 days | compilaton of collected data an public comment
2003-02-02 | Data Compilation | 2003-02-20 | Data Compilation
20 days | Constituencies work out there positions | 30 days | Constituencies work out there positions
2003-02-23 | Constituency statements | 21. March | Constituency statements
9 days | Input summary prepared pre ICANN Rome | 10 days | Input summary prepared
02. March | Input summary | 31. March | Input summary
20 days | Task Force prepares Preliminary Report. | 20 days | Task Force prepares Preliminary Report.
22. March | Preliminary Report; start public comment. | 2003-04-20 | Preliminary Report
20 days | Public comment period | 20 days | Public comment period
10 days | Task Force prepares Final Report. | 2003-05-10 | End Public Comment
2003-04-22 | Final Report | 10 days | Task Force prepares Final Report.
|  | 2003-04-20 | Final Report